## Milestone Reporting Form Page 1
Successor Solar Incentive (SuSI) Program
Administratively Determined Incentive (ADI) Program
Milestone Reporting Form
For All Net Metered Non-Residential Facilities 1 MW (dc) or larger
| Initial Report Date: |  |  | OR | Report for Quarter Ending:
PROGRAM TERMS AND CONDITIONS
Registrants in the Administratively Determined Incentive Program (ADI) must comply with all ADI terms and conditions, eligibility requirements and installation requirements, and submit all completed forms. This Milestone Reporting Form must be submitted by the Registrant as an initial report with the ADI Registration Packet and quarterly thereafter until the Post Construction Certification (Final As- Built) packet is submitted. Quarterly reports must be submitted to the ADI Processing Team at njreinfo@njcleanenergy.com within two weeks of the quarters ending March 31, June 30, September 30 and December 31.Timely submission of Milestone Reporting Forms will be considered in the evaluation of an extension request.
INSTRUCTIONS FOR COMPLETING THIS FORM
The Milestone Reporting Form is required to be submitted for all Net Metered Facilities 1 MW (dc) or larger that have submitted a complete ADI Registration Packet and been issued a ADI Conditional Acceptance letter. Net Metered Non-Residential Solar Facilities participating in the ADI Program cannot exceed 5 MW (dc).
Section B: | Please complete the chart, indicating whether each of the listed project milestones has been achieved. Where a milestone has been achieved, please insert the date it occurred in the Date Achieved column (it is not necessary to submit any supporting documentation); where a milestone has not been achieved, please insert the date that you expect it to occur in the Date Expected to Achieve column. Dates may be expressed as month and year; it is not necessary to identify a particular day. Please use the Comments section to elaborate on any of your responses.
Section C: | The Primary Contact (SREC-II Owner) and Premise Contact (if different from the SREC-II Owner) must sign the appropriate space(s).
Once this form is completed, it should be uploaded in the ADI online registration portal as part of the ADI Initial Registration Packet submission. Quarterly submissions can be sent to njreinfo@njcleanenergy.com.
NOTE: If the Change in Original SREC- II Ownership box is checked below, a copy of the most recent disclosure form must be submitted to the ADI Processing Team together with a revised ADI Registration Certification Form.
SECTION A: PREMISE CONTACT AND PROJECT IDENTIFICATION
ADI Registration Number: |  |  |  | Utility Account Number
System Size kW (dc): |  | Original |  |  | Revised |  | (decrease only)
Name of Primary Contact (SREC-II Owner): | [5 empty] | Change in Original SREC-II Owner
Name of Company or Organization:
Installation Address:
City, State, ZIP Code: |  | (City) |  |  | (State) |  | (ZIP Code)
Daytime Phone: |  |  |  |  | Email Address:
Name of Premise Contact (if different from SREC-II Owner):
Name of Company or Organization:
Address:
City, State, ZIP Code: |  | (City) |  |  | (State) |  | (ZIP Code)
Daytime Phone: |  |  |  |  | Email Address:

## Milestone Reporting Form Page 2
Successor Solar Incentive (SuSI) Program
Administratively Determined Incentive (ADI) Program
Milestone Reporting Form
For All Net Metered Non Residential Facilities 1 MW (dc) or larger
SECTION B: PROJECT MILESTONES
Milestone |  |  | Achieved (Y / N) | Date Achieved | Date Expected to Achieve
1 | Submitted interconnection application to EDC
2 | All required federal, state and local permits obtained
3 | Received interconnection application approval from EDC
4 | Mounting system installation has begun
5 | Mounting system installed
6 | Greater than 50% of solar panels installed
7 | All equipment installed, system testing complete and request sent to EDC to test and authorize operation of system
8 | EDC Authorization to Operate Approval
NOTE: If items #1-7 above have been achieved, what still remains to be completed to obtain the approval for the authorization to operate from the EDC?
SECTION C: CERTIFICATIONS
The undersigned warrants, certifies and represents that the information provided in this form is true and correct to the best of his or her knowledge.
I agree that this document and all notices and disclosures made or given relating to this document may be created, executed, delivered and retained electronically and that the electronic signatures appearing on this document and any related documents shall have the same legal effect for all purposes as a handwritten signature.
The information, statements, and documents I have provided in and with this document are true and accurate to the best of my knowledge. I am aware that if any of them are willfully false, I am subject to punishment.
IF USING AN ELECTRONIC SIGNATURE, PLEASE UPLOAD IN THE ADI ONLINE PORTAL THE CERTIFICATION OF COMPLETION OR THE SIGNATURE VERIFICATION SHEET.
Primary Contact (SREC-II Owner) |  |  | Premise Contact (if different from SREC-II Owner)
Signature: |  |  | Signature:
Print Name: |  |  | Print Name:
Date: |  |  | Date: